## final table
taskID | task | predecessorTaskIDs | best case hours | expected hours | worst case hours | worst case hours with independent contractor | best case cost | expected cost | worst case cost | assigned associate | worst case cost with independent contractor | assigned associate
A | Describe product |  | 7.2 | 8 | 8.8 | 8.8 | 720 | 800 | 880 | Anhua Cheng | 880 | Anhua Cheng
B | Develop marketing strategy |  | 36 | 40 | 44 | 44 | 3600 | 4000 | 4400 | Rebecca Bailey Scoville | 4400 | Rebecca Bailey Scoville
C | Design brochure | A | 36 | 40 | 44 | 44 | 3600 | 4000 | 4400 | Rebecca Bailey Scoville | 4400 | Rebecca Bailey Scoville
D | Develop product prototype (min completion time) |  | 302.4 | 336 | 369.6 | 193.6 | 30240 | 33600 | 36960 |  | 19360
D1 | Requirements analysis | A | 14.4 | 16 | 17.6 | 17.6 | 1440 | 1600 | 1760 | Anhua Cheng | 1760 | Anhua Cheng
D2 | Software design | D1 | 108 | 120 | 132 | 66 | 10800 | 12000 | 13200 | Griffin Arnone | 19800 | Griffin Arnone + Contractor
D3 | System design | D1 | 36 | 40 | 44 | 44 | 3600 | 4000 | 4400 | Anhua Cheng | 4400 | Anhua Cheng
D4 | Coding | D2, D3 | 72 | 80 | 88 | 44 | 7200 | 8000 | 8800 | Griffin Arnone | 13200 | Griffin Arnone + Contractor
D5 | Write documentation | D4 | 36 | 40 | 44 | 44 | 3600 | 4000 | 4400 | Griffin Arnone | 4400 | Griffin Arnone
D6 | Unit testing | D4 | 36 | 40 | 44 | 22 | 3600 | 4000 | 4400 | Anhua Cheng | 6600 | Anhua Cheng + Contractor
D7 | System testing | D6 | 36 | 40 | 44 | 22 | 3600 | 4000 | 4400 | Anhua Cheng | 6600 | Anhua Cheng + Contractor
D8 | Package deliverables | D5, D7 | 36 | 40 | 44 | 22 | 3600 | 4000 | 4400 | Anhua Cheng | 6600 | Anhua Cheng + Contractor
E | Survey potential market | B, C | 36 | 40 | 44 | 44 | 3600 | 4000 | 4400 | Rebecca Bailey Scoville | 4400 | Rebecca Bailey Scoville
F | Develop pricing plan | D8, E | 21.6 | 24 | 26.4 | 26.4 | 2160 | 2400 | 2640 | Rebecca Bailey Scoville | 2640 | Rebecca Bailey Scoville
G | Develop implementation plan | A, D8 | 21.6 | 24 | 26.4 | 26.4 | 2160 | 2400 | 2640 | Anhua Cheng | 2640 | Anhua Cheng
H | Write client proposal | F, G | 36 | 40 | 44 | 44 | 3600 | 4000 | 4400 | Rebecca Bailey Scoville | 4400 | Rebecca Bailey Scoville
| Subtotal |  | 568.8 | 632 | 695.2 |  | 56880 | 63200 | 69520 |  | 87120

## expected
input cells
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 7.2 | 8 | 8.8
B | Develop marketing strategy |  | 36 | 40 | 44
C | Design brochure | A | 36 | 40 | 44
D | Develop product prototype |  |  | 336
D1 | Requirements analysis | A | 14.4 | 16 | 17.6
D2 | Software design | D1 | 108 | 120 | 132
D3 | System design | D1 | 36 | 40 | 44
D4 | Coding | D2, D3 | 72 | 80 | 88
D5 | Write documentation | D4 | 36 | 40 | 44
D6 | Unit testing | D4 | 36 | 40 | 44
D7 | System testing | D6 | 36 | 40 | 44
D8 | Package deliverables | D5, D7 | 36 | 40 | 44
E | Survey potential market | B, C | 36 | 40 | 44
F | Develop pricing plan | D8, E | 21.6 | 24 | 26.4
G | Develop implementation plan | A, D8 | 21.6 | 24 | 26.4
H | Write client proposal | F, G | 36 | 40 | 44
D. Develop product prototype
Decision Variables |  | Changing Cells
|  | d0 | d1 | d2 | d3 | d4 | d5 | d6 | d7 | d8
|  | 0 | 16 | 136 | 56 | 216 | 296 | 256 | 296 | 336
Objective |  | Changing Cells d0: Objective Cell
| minimize completion time | Changing Cells d0: 336
Constraints (expected hours) | Node 0 to Node 1 | [9 empty] | 16 | >= | 16 | bar: Changing Cells d0 to Changing Cells d1
| Node 1 to Node 2 | [9 empty] | 120 | >= | 120 | bar: Changing Cells d1 to Changing Cells d2
| Node 1 to Node 3 | [9 empty] | 40 | >= | 40 | bar: Changing Cells d1; Changing Cells d3
| Node 3 to Node 2 | [9 empty] | 80 | >= | 0 | bar: Changing Cells d2 to Changing Cells d3
| Node 2 to Node 4 | [9 empty] | 80 | >= | 80 | bar: Changing Cells d2; Changing Cells d4
| Node 4 to Node 5 | [9 empty] | 80 | >= | 40 | bar: Changing Cells d4 to Changing Cells d5
| Node 4 to Node 6 | [9 empty] | 40 | >= | 40 | bar: Changing Cells d4; Changing Cells d6
| Node 6 to Node 7 | [9 empty] | 40 | >= | 40 | bar: Changing Cells d6 to Changing Cells d7
| Node 7 to Node 5 | [9 empty] | 0 | >= | 0 | bar: Changing Cells d5; Changing Cells d7
| Node 5 to Node 8 | [9 empty] | 40 | >= | 40 | bar: Changing Cells d5; Changing Cells d8
Website Development
Decision Variables |  | Changing Cells d0: Changing Cells
|  | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9
|  | 0 | 8 | 304 | 304 | 344 | 344 | 368 | 368 | 344 | 408
Objective |  | Changing Cells t0: Objective Cell
| minimize completion time | Changing Cells t0: 408
Constraints (expected hours) | Node 0 to Node 1 | [10 empty] | 8 | >= | 8 | bar: Changing Cells t0 to Changing Cells t1
| Node 0 to Node 2 | [10 empty] | 304 | >= | 40 | bar: Changing Cells t0; Changing Cells t2
| Node 1 to Node 4 | [10 empty] | 336 | >= | 336 | bar: Changing Cells t1; Changing Cells t4
| Node 1 to Node 3 | [10 empty] | 296 | >= | 40 | bar: Changing Cells t1; Changing Cells t3
| Node 2 to Node 3 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t2 to Changing Cells t3
| Node 4 to Node 7 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4; Changing Cells t8
| Node 4 to Node 5 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4 to Changing Cells t5
| Node 3 to Node 5 | [10 empty] | 40 | >= | 40 | bar: Changing Cells t3; Changing Cells t5
| Node 5 to Node 6 | [10 empty] | 24 | >= | 24 | bar: Changing Cells t5 to Changing Cells t6
| Node 7 to Node 8 | [10 empty] | 24 | >= | 24 | bar: Changing Cells t7 to Changing Cells t8
| Node 6 to Node 8 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t6 to Changing Cells t7
| Node 1 to Node 7 | [10 empty] | 336 | >= | 0 | bar: Changing Cells t1; Changing Cells t8
| Node 8 to Node 9 | [10 empty] | 40 | >= | 40 | bar: Changing Cells t7; Changing Cells t9

## best
input cells
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 7.2 | 8 | 8.8
B | Develop marketing strategy |  | 36 | 40 | 44
C | Design brochure | A | 36 | 40 | 44
D | Develop product prototype |  | 302.4 | 336
D1 | Requirements analysis | A | 14.4 | 16 | 17.6
D2 | Software design | D1 | 108 | 120 | 132
D3 | System design | D1 | 36 | 40 | 44
D4 | Coding | D2, D3 | 72 | 80 | 88
D5 | Write documentation | D4 | 36 | 40 | 44
D6 | Unit testing | D4 | 36 | 40 | 44
D7 | System testing | D6 | 36 | 40 | 44
D8 | Package deliverables | D5, D7 | 36 | 40 | 44
E | Survey potential market | B, C | 36 | 40 | 44
F | Develop pricing plan | D8, E | 21.6 | 24 | 26.4
G | Develop implementation plan | A, D8 | 21.6 | 24 | 26.4
H | Write client proposal | F, G | 36 | 40 | 44
D. Develop product prototype
Decision Variables |  | Changing Cells
|  | d0 | d1 | d2 | d3 | d4 | d5 | d6 | d7 | d8
|  | 0 | 14.4 | 122.4 | 50.4 | 194.4 | 266.4 | 230.4 | 266.4 | 302.4
Objective |  | Changing Cells d0: Objective Cell
| minimize completion time | Changing Cells d0: 302.4
Constraints (expected hours) | Node 0 to Node 1 | [9 empty] | 14.4 | >= | 14.4 | bar: Changing Cells d0 to Changing Cells d1
| Node 1 to Node 2 | [9 empty] | 108 | >= | 108 | bar: Changing Cells d1 to Changing Cells d2
| Node 1 to Node 3 | [9 empty] | 36 | >= | 36 | bar: Changing Cells d1; Changing Cells d3
| Node 3 to Node 2 | [9 empty] | 72 | >= | 0 | bar: Changing Cells d2 to Changing Cells d3
| Node 2 to Node 4 | [9 empty] | 72 | >= | 72 | bar: Changing Cells d2; Changing Cells d4
| Node 4 to Node 5 | [9 empty] | 72 | >= | 36 | bar: Changing Cells d4 to Changing Cells d5
| Node 4 to Node 6 | [9 empty] | 36 | >= | 36 | bar: Changing Cells d4; Changing Cells d6
| Node 6 to Node 7 | [9 empty] | 36 | >= | 36 | bar: Changing Cells d6 to Changing Cells d7
| Node 7 to Node 5 | [9 empty] | 0 | >= | 0 | bar: Changing Cells d5; Changing Cells d7
| Node 5 to Node 8 | [9 empty] | 36 | >= | 36 | bar: Changing Cells d5; Changing Cells d8
Website Development
Decision Variables |  | Changing Cells d0: Changing Cells
|  | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9
|  | 0 | 7.2 | 273.6 | 273.6 | 309.6 | 309.6 | 331.2 | 331.2 | 309.6 | 367.2
Objective |  | Changing Cells t0: Objective Cell
| minimize completion time | Changing Cells t0: 367.2
Constraints (expected hours) | Node 0 to Node 1 | [10 empty] | 7.2 | >= | 7.2 | bar: Changing Cells t0 to Changing Cells t1
| Node 0 to Node 2 | [10 empty] | 273.6 | >= | 36 | bar: Changing Cells t0; Changing Cells t2
| Node 1 to Node 4 | [10 empty] | 302.4 | >= | 302.4 | bar: Changing Cells t1; Changing Cells t4
| Node 1 to Node 3 | [10 empty] | 266.4 | >= | 36 | bar: Changing Cells t1; Changing Cells t3
| Node 2 to Node 3 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t2 to Changing Cells t3
| Node 4 to Node 7 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4; Changing Cells t8
| Node 4 to Node 5 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4 to Changing Cells t5
| Node 3 to Node 5 | [10 empty] | 36 | >= | 36 | bar: Changing Cells t3; Changing Cells t5
| Node 5 to Node 6 | [10 empty] | 21.6 | >= | 21.6 | bar: Changing Cells t5 to Changing Cells t6
| Node 7 to Node 8 | [10 empty] | 21.6 | >= | 21.6 | bar: Changing Cells t7 to Changing Cells t8
| Node 6 to Node 8 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t6 to Changing Cells t7
| Node 1 to Node 7 | [10 empty] | 302.4 | >= | 0 | bar: Changing Cells t1; Changing Cells t8
| Node 8 to Node 9 | [10 empty] | 36 | >= | 36 | bar: Changing Cells t7; Changing Cells t9

## worst
input cells
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 7.2 | 8 | 8.8
B | Develop marketing strategy |  | 36 | 40 | 44
C | Design brochure | A | 36 | 40 | 44
D | Develop product prototype |  | 302.4 | 336 | 369.6
D1 | Requirements analysis | A | 14.4 | 16 | 17.6
D2 | Software design | D1 | 108 | 120 | 132
D3 | System design | D1 | 36 | 40 | 44
D4 | Coding | D2, D3 | 72 | 80 | 88
D5 | Write documentation | D4 | 36 | 40 | 44
D6 | Unit testing | D4 | 36 | 40 | 44
D7 | System testing | D6 | 36 | 40 | 44
D8 | Package deliverables | D5, D7 | 36 | 40 | 44
E | Survey potential market | B, C | 36 | 40 | 44
F | Develop pricing plan | D8, E | 21.6 | 24 | 26.4
G | Develop implementation plan | A, D8 | 21.6 | 24 | 26.4
H | Write client proposal | F, G | 36 | 40 | 44
D. Develop product prototype
Decision Variables |  | Changing Cells
|  | d0 | d1 | d2 | d3 | d4 | d5 | d6 | d7 | d8
|  | 0 | 17.6 | 149.6 | 61.6 | 237.6 | 325.6 | 281.6 | 325.6 | 369.6
Objective |  | Changing Cells d0: Objective Cell
| minimize completion time | Changing Cells d0: 369.6
Constraints (expected hours) | Node 0 to Node 1 | [9 empty] | 17.6 | >= | 17.6 | bar: Changing Cells d0 to Changing Cells d1
| Node 1 to Node 2 | [9 empty] | 132 | >= | 132 | bar: Changing Cells d1 to Changing Cells d2
| Node 1 to Node 3 | [9 empty] | 44 | >= | 44 | bar: Changing Cells d1; Changing Cells d3
| Node 3 to Node 2 | [9 empty] | 88 | >= | 0 | bar: Changing Cells d2 to Changing Cells d3
| Node 2 to Node 4 | [9 empty] | 88 | >= | 88 | bar: Changing Cells d2; Changing Cells d4
| Node 4 to Node 5 | [9 empty] | 88 | >= | 44 | bar: Changing Cells d4 to Changing Cells d5
| Node 4 to Node 6 | [9 empty] | 44 | >= | 44 | bar: Changing Cells d4; Changing Cells d6
| Node 6 to Node 7 | [9 empty] | 44 | >= | 44 | bar: Changing Cells d6 to Changing Cells d7
| Node 7 to Node 5 | [9 empty] | 0 | >= | 0 | bar: Changing Cells d5; Changing Cells d7
| Node 5 to Node 8 | [9 empty] | 44 | >= | 44 | bar: Changing Cells d5; Changing Cells d8
Website Development
Decision Variables |  | Changing Cells d0: Changing Cells
|  | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9
|  | 0 | 8.8 | 334.4 | 334.4 | 378.4 | 378.4 | 404.8 | 404.8 | 378.4 | 448.8
Objective |  | Changing Cells t0: Objective Cell
| minimize completion time | Changing Cells t0: 448.8
Constraints (expected hours) | Node 0 to Node 1 | [10 empty] | 8.8 | >= | 8.8 | bar: Changing Cells t0 to Changing Cells t1
| Node 0 to Node 2 | [10 empty] | 334.4 | >= | 44 | bar: Changing Cells t0; Changing Cells t2
| Node 1 to Node 4 | [10 empty] | 369.6 | >= | 369.6 | bar: Changing Cells t1; Changing Cells t4
| Node 1 to Node 3 | [10 empty] | 325.6 | >= | 44 | bar: Changing Cells t1; Changing Cells t3
| Node 2 to Node 3 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t2 to Changing Cells t3
| Node 4 to Node 7 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4; Changing Cells t8
| Node 4 to Node 5 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4 to Changing Cells t5
| Node 3 to Node 5 | [10 empty] | 44 | >= | 44 | bar: Changing Cells t3; Changing Cells t5
| Node 5 to Node 6 | [10 empty] | 26.4 | >= | 26.4 | bar: Changing Cells t5 to Changing Cells t6
| Node 7 to Node 8 | [10 empty] | 26.4 | >= | 26.4 | bar: Changing Cells t7 to Changing Cells t8
| Node 6 to Node 8 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t6 to Changing Cells t7
| Node 1 to Node 7 | [10 empty] | 369.6 | >= | 0 | bar: Changing Cells t1; Changing Cells t8
| Node 8 to Node 9 | [10 empty] | 44 | >= | 44 | bar: Changing Cells t7; Changing Cells t9

## worst v2
input cells
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 7.2 | 8 | 8.8
B | Develop marketing strategy |  | 36 | 40 | 44
C | Design brochure | A | 36 | 40 | 44
D | Develop product prototype |  |  |  | 193.6
D1 | Requirements analysis | A | 14.4 | 16 | 17.6
D2 | Software design | D1 | 54 | 60 | 66
D3 | System design | D1 | 36 | 40 | 44
D4 | Coding | D2, D3 | 36 | 40 | 44
D5 | Write documentation | D4 | 36 | 40 | 44
D6 | Unit testing | D4 | 18 | 20 | 22
D7 | System testing | D6 | 18 | 20 | 22
D8 | Package deliverables | D5, D7 | 18 | 20 | 22
E | Survey potential market | B, C | 36 | 40 | 44
F | Develop pricing plan | D8, E | 21.6 | 24 | 26.4
G | Develop implementation plan | A, D8 | 21.6 | 24 | 26.4
H | Write client proposal | F, G | 36 | 40 | 44
D. Develop product prototype
Decision Variables |  | Changing Cells
|  | d0 | d1 | d2 | d3 | d4 | d5 | d6 | d7 | d8
|  | 0 | 17.6 | 83.6 | 61.6 | 127.6 | 171.6 | 149.6 | 171.6 | 193.6
Objective |  | Changing Cells d0: Objective Cell
| minimize completion time | Changing Cells d0: 193.6
Constraints (expected hours) | Node 0 to Node 1 | [9 empty] | 17.6 | >= | 17.6 | bar: Changing Cells d0 to Changing Cells d1
| Node 1 to Node 2 | [9 empty] | 66 | >= | 66 | bar: Changing Cells d1 to Changing Cells d2
| Node 1 to Node 3 | [9 empty] | 44 | >= | 44 | bar: Changing Cells d1; Changing Cells d3
| Node 3 to Node 2 | [9 empty] | 22 | >= | 0 | bar: Changing Cells d2 to Changing Cells d3
| Node 2 to Node 4 | [9 empty] | 44 | >= | 44 | bar: Changing Cells d2; Changing Cells d4
| Node 4 to Node 5 | [9 empty] | 44 | >= | 44 | bar: Changing Cells d4 to Changing Cells d5
| Node 4 to Node 6 | [9 empty] | 22 | >= | 22 | bar: Changing Cells d4; Changing Cells d6
| Node 6 to Node 7 | [9 empty] | 22 | >= | 22 | bar: Changing Cells d6 to Changing Cells d7
| Node 7 to Node 5 | [9 empty] | 0 | >= | 0 | bar: Changing Cells d5; Changing Cells d7
| Node 5 to Node 8 | [9 empty] | 22 | >= | 22 | bar: Changing Cells d5; Changing Cells d8
Website Development
Decision Variables |  | Changing Cells d0: Changing Cells
|  | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9
|  | 0 | 8.8 | 158.4 | 158.4 | 202.4 | 202.4 | 228.8 | 228.8 | 202.4 | 272.8
Objective |  | Changing Cells t0: Objective Cell
| minimize completion time | Changing Cells t0: 272.8
Constraints (expected hours) | Node 0 to Node 1 | [10 empty] | 8.8 | >= | 8.8 | bar: Changing Cells t0 to Changing Cells t1
| Node 0 to Node 2 | [10 empty] | 158.4 | >= | 44 | bar: Changing Cells t0; Changing Cells t2
| Node 1 to Node 4 | [10 empty] | 193.6 | >= | 193.6 | bar: Changing Cells t1; Changing Cells t4
| Node 1 to Node 3 | [10 empty] | 149.6 | >= | 44 | bar: Changing Cells t1; Changing Cells t3
| Node 2 to Node 3 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t2 to Changing Cells t3
| Node 4 to Node 7 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4; Changing Cells t8
| Node 4 to Node 5 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t4 to Changing Cells t5
| Node 3 to Node 5 | [10 empty] | 44 | >= | 44 | bar: Changing Cells t3; Changing Cells t5
| Node 5 to Node 6 | [10 empty] | 26.4 | >= | 26.4 | bar: Changing Cells t5 to Changing Cells t6
| Node 7 to Node 8 | [10 empty] | 26.4 | >= | 26.4 | bar: Changing Cells t7 to Changing Cells t8
| Node 6 to Node 8 | [10 empty] | 0 | >= | 0 | bar: Changing Cells t6 to Changing Cells t7
| Node 1 to Node 7 | [10 empty] | 193.6 | >= | 0 | bar: Changing Cells t1; Changing Cells t8
| Node 8 to Node 9 | [10 empty] | 44 | >= | 44 | bar: Changing Cells t7; Changing Cells t9